## Sheet1
Resource Name:
Team: | ATM Dashboard v2
Year-Month: | 2020-March
Task Name |  | 2020-03-16 | 2020-03-17 | 2020-03-18 | 2020-03-19 | 2020-03-20 | 2020-03-21 | 2020-03-22 | 2020-03-23 | 2020-03-24 | 2020-03-25 | 2020-03-26 | 2020-03-27 | 2020-03-28 | 2020-03-29 | 2020-03-30 | 2020-03-31
Project Task |  | 6 | 0 | 0 | 0 | 8 | 8 | 8 | 8 | 8 | 9 | 12 | 10 | 8 | 8 | 8 | 12 | 113
Learned subqueries |  | 2020-03-16: 3 | 3
Trial and testing of own subqueries | [17 empty] | 1 | bar: 2020-03-16
Tried to test created queries on the system |  | 2020-03-16: 2 | 2
Early Dismissal |  | 2020-03-16: 0 | 0
EL |  | 2020-03-17: 0 | 0
EL |  | 2020-03-18: 0 | 0
EL |  | 2020-03-19: 0 | 0
Downloaded necessary application to set-up |  | 2020-03-20: 8 | 8
Setup database |  | 2020-03-21: 4 | 4
Setup tables |  | 2020-03-21: 4 | 4
Fixed java spring issues |  | 2020-03-22: 2 | 2
coded test controller, model and repo |  | 2020-03-22: 4 | 4
Studied more on java spring |  | 2020-03-22: 2 | 2
Learned to import excel data to PgAdmin |  | 2020-03-23: 8 | 8
Studied d3.js |  | 2020-03-24: 8 | 8
Studied d3.js with more examples and code application |  | 2020-03-25: 9 | 9
Created dummy data to experiment on d3.js |  | 2020-03-26: 4 | 4
Studied other form of charts of d3.js |  | 2020-03-26: 6 | 6
Tried to use generated JSON from java to d3 |  | 2020-03-27: 8 | 8
Studied different kinds of executing JSON |  | 2020-03-28: 8 | 8
Testing of trying to use generated JSON |  | 2020-03-29: 8 | 8
Learned ajax to use generated JSON |  | 2020-03-30: 8 | 8
Experimented on ways to use the generated JSON by using javascript |  | 2020-03-31: 12 | 12
0
0
0
0
0
0
0
Meetings |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 7
7 | bar: 2020-03-23 to 2020-03-27; 2020-03-30 to 2020-03-31
0
Admin Task |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0
0
Trainings |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0
0
0
Leaves |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Sick Leave | [17 empty] | 0
Vacation Leave | [17 empty] | 0
Mandatory Leave | [17 empty] | 0
Holidays |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0
0
|  | 6 | 0 | 0 | 0 | 8 | 8 | 8 | 9 | 9 | 10 | 13 | 11 | 8 | 8 | 9 | 13 | X