## Summary
Row Labels | E Start Date | E End Date | Sum of Estimated Hours | A Start Date | A End Date | Sum of Actual Hours | Average of % Completed
Analysis | 2020-03-20 | 2020-03-20 | 192 | 2020-03-20 | 2020-03-20 | 32 | 100%
Angelo Ancheta | 2020-03-23 | 2020-03-23 | 48 | 2020-03-23 | 2020-03-23 | 8 | 100%
Project Requirements Setup | 2020-03-23 | 2020-03-23 | 8 | 2020-03-23 | 2020-03-23 | 8 | 100%
Research and Familiarization | 2020-03-23 | 2020-03-27 | 40 | 2020-03-23 |  |  | 100%
Danielle Leones | 2020-03-20 | 2020-03-20 | 48 | 2020-03-20 | 2020-03-20 | 8 | 100%
Project Requirements Setup | 2020-03-20 | 2020-03-20 | 8 | 2020-03-20 | 2020-03-20 | 8 | 100%
Research and Familiarization | 2020-03-20 | 2020-03-27 | 40 |  |  |  | 100%
Elijah Leis | 2020-03-20 | 2020-03-20 | 48 | 2020-03-20 | 2020-03-20 | 8 | 100%
Project Requirements Setup | 2020-03-20 | 2020-03-20 | 8 | 2020-03-20 | 2020-03-20 | 8 | 100%
Research and Familiarization | 2020-03-23 | 2020-03-27 | 40 | 2020-03-23 |  |  | 100%
Frank Tabayay | 2020-03-20 | 2020-03-20 | 48 | 2020-03-20 | 2020-03-20 | 8 | 100%
Project Requirements Setup | 2020-03-20 | 2020-03-20 | 8 | 2020-03-20 | 2020-03-20 | 8 | 100%
Research and Familiarization | 2020-03-23 | 2020-03-27 | 40 |  |  |  | 100%
Implementation | 2020-03-23 | 2020-04-24 |  | 2020-03-23 |  |  | 10%
Angelo Ancheta | 2020-03-23 | 2020-04-30 |  | 2020-03-23 |  |  | 10%
Actual Coding | 2020-03-23 | 2020-04-30 |  | 2020-03-23 |  |  | 10%
Danielle Leones | 2020-03-23 | 2020-05-01 |  | 2020-03-23 |  |  | 10%
Actual Coding | 2020-03-23 | 2020-05-01 |  | 2020-03-23 |  |  | 10%
Elijah Leis | 2020-03-23 | 2020-04-30 |  | 2020-03-23 |  |  | 5%
Actual Coding | 2020-03-23 | 2020-04-30 |  | 2020-03-23 |  |  | 5%
Frank Tabayay | 2020-03-23 | 2020-04-24 |  | 2020-03-23 |  |  | 15%
Actual Coding | 2020-03-23 | 2020-04-24 |  | 2020-03-23 |  |  | 15%
Testing | 2020-04-03 | 2020-04-24 |  |  |  |  | 0%
Angelo Ancheta | 2020-04-03 | 2020-04-30 |  |  |  |  | 0%
Unit Testing and SonarQube Fixes | 2020-04-03 | 2020-04-30 |  |  |  |  | 0%
Danielle Leones | 2020-04-03 | 2020-05-03 |  |  |  |  | 0%
Unit Testing and SonarQube Fixes | 2020-04-03 | 2020-05-03 |  |  |  |  | 0%
Elijah Leis | 2020-04-03 | 2020-04-30 |  |  |  |  | 0%
Unit Testing and SonarQube Fixes | 2020-04-03 | 2020-04-30 |  |  |  |  | 0%
Frank Tabayay | 2020-04-03 | 2020-04-24 |  |  |  |  | 0%
Unit Testing and SonarQube Fixes | 2020-04-03 | 2020-04-24 |  |  |  |  | 0%
(blank)
Grand Total | 2020-03-20 | 2020-03-20 | 192 | 2020-03-20 | 2020-03-20 | 32 | 52.5%

## Impact Analysis and Estimate
Impact Analysis & Estimate
Project Name: | CAM Dashboard
Task Ref # | Task Name | Task Description | Phase | Assigned To | Estimated Start Date | Estimated End Date | Estimated Hours | Actual Start Date | Actual End Date | Actual Hours | % Completed
1 | CAM Dashboard | Project Requirements Setup | Analysis | Elijah Leis | 2020-03-20 | 2020-03-20 | 8 | 2020-03-20 | 2020-03-20 | 8 | 100%
2 | CAM Dashboard | Research and Familiarization | Analysis | Elijah Leis | 2020-03-23 | 2020-03-27 | 40 | 2020-03-23 |  |  | 100%
3 | CAM Dashboard | Actual Coding | Implementation | Elijah Leis | 2020-03-23 | 2020-04-30 |  | 2020-03-23 |  |  | 5%
4 | CAM Dashboard | Unit Testing and SonarQube Fixes | Testing | Elijah Leis | 2020-04-03 | 2020-04-30 |  |  |  |  | 0%
5 | CAM Inventory with Machine Profile | Project Requirements Setup | Analysis | Danielle Leones | 2020-03-20 | 2020-03-20 | 8 | 2020-03-20 | 2020-03-20 | 8 | 100%
6 | CAM Inventory with Machine Profile | Research and Familiarization | Analysis | Danielle Leones | 2020-03-20 | 2020-03-27 | 40 |  |  |  | 100%
7 | CAM Inventory with Machine Profile | Actual Coding | Implementation | Danielle Leones | 2020-03-23 | 2020-05-01 |  | 2020-03-23 |  |  | 10%
8 | CAM Inventory with Machine Profile | Unit Testing and SonarQube Fixes | Testing | Danielle Leones | 2020-04-03 | 2020-05-03 |  |  |  |  | 0%
9 | CAM Cash Flow Monitoring | Project Requirements Setup | Analysis | Frank Tabayay | 2020-03-20 | 2020-03-20 | 8 | 2020-03-20 | 2020-03-20 | 8 | 100%
10 | CAM Cash Flow Monitoring | Research and Familiarization | Analysis | Frank Tabayay | 2020-03-23 | 2020-03-27 | 40 |  |  |  | 100%
11 | CAM Cash Flow Monitoring | Actual Coding | Implementation | Frank Tabayay | 2020-03-23 | 2020-04-24 |  | 2020-03-23 |  |  | 15%
12 | CAM Cash Flow Monitoring | Unit Testing and SonarQube Fixes | Testing | Frank Tabayay | 2020-04-03 | 2020-04-24 |  |  |  |  | 0%
13 | Nearest Branch/Machine Locator | Project Requirements Setup | Analysis | Angelo Ancheta | 2020-03-23 | 2020-03-23 | 8 | 2020-03-23 | 2020-03-23 | 8 | 100%
14 | Nearest Branch/Machine Locator | Research and Familiarization | Analysis | Angelo Ancheta | 2020-03-23 | 2020-03-27 | 40 | 2020-03-23 |  |  | 100%
15 | Nearest Branch/Machine Locator | Actual Coding | Implementation | Angelo Ancheta | 2020-03-23 | 2020-04-30 |  | 2020-03-23 |  |  | 10%
16 | Nearest Branch/Machine Locator | Unit Testing and SonarQube Fixes | Testing | Angelo Ancheta | 2020-04-03 | 2020-04-30 |  |  |  |  | 0%

## Requirements
Requirements
I. CAM Dashboard |  | Change Request History
| a. Load visualizations to show availability and downtime of CAMs | Date | Change In | Changed By
| b. Filter chart results by date range | 2020-04-02 | Initial document | Samantha Forlaje
c. Visualizations can be exported as PDF
II. CAM Inventory with Machine Profile
a. Display CAM Inventory
b. ATM Profile (pop-up) upon machine select containing complete invetory details
c. Implement inventory CRUD functions. Decommission machine instead of Deletion.
d. Machine Filtering
e. Export Inventory as PDF
III. CAM Cash Flow Monitoring
a. Filtering (machine_id or location)
b. Machine Cash Flow Reporting
c. CAM Money Unloading History
d. Availability-Amount Accepted report
IV. Nearest Branch/Machine Locator
a. Location Filter resulting to nearest branch/machine results
b. Nearest Branch - should be open and operational Nearest Terminal - should be online and available
c. Display availability, address and operational hrs of branch/machine upon select
d. Create microservice that translates address to coordinates

## LookupTable (hidden)
Resources | Phases
Jhoan Dignadice | Analysis
Sam Forlaje | Design
Angelo Ancheta | Implementation
Elijah Leis | Testing
Danielle Leones | Deployment
Frank Tabayay

## Chart Data (hidden)
% Completed | 52.5%
% Remaining | 47.5%