## Sheet1
Resource Name:
Team: | ATM Dashboard v2
Year-Month: | 2020-March
Task Name |  | 2020-04-01 | 2020-04-02 | 2020-04-03 | 2020-04-04 | 2020-04-05 | 2020-04-06 | 2020-04-07 | 2020-04-08 | 2020-04-09 | 2020-04-10 | 2020-04-11 | 2020-04-12 | 2020-04-13 | 2020-04-14 | 2020-04-15 | 2020-04-16 | 2020-04-17 | 2020-04-18 | 2020-04-19 | 2020-04-20 | 2020-04-21 | 2020-04-22 | 2020-04-23 | 2020-04-24 | 2020-04-25 | 2020-04-26 | 2020-04-27 | 2020-04-28 | 2020-04-29 | 2020-04-30
Project Task |  | 8 | 10 | 20 | 4 | 4 | 8 | 19 | 10 | 5 | 12 | 0 | 0 | 9 | 9 | 10 | 13 | 10 | 0 | 0 | 12 | 18 | 9 | 16 | 5 | 0 | 0 | 8 | 0 | 0 | 0 | 219
Studied Bootstrap |  | 2020-04-01: 8 | 8
Created initial design |  | 2020-04-02: 10 | 10
Learned other chart to try and replace d3 |  | 2020-04-03: 14 | 14
Try to experiment on different charts while studying d3 furthermore |  | 2020-04-03: 6 | 6
Coded the bar chart on the initial design of website |  | 2020-04-06: 8 | 8
Research on proper dashboard design |  | 2020-04-07: 8 | 8
Coded the proper dashboard design and integrate chart |  | 2020-04-07: 4 | 4
Review for the exam |  | 2020-04-04: 4; 2020-04-05: 4; 2020-04-07: 4 | 12
Exam | [31 empty] | 1 | bar: 2020-04-07
Fixing git problems on my side |  | 2020-04-07: 2 | 2
Studied D3.js using pie chart |  | 2020-04-08: 5 | 5
Coded pie chart using sample data |  | 2020-04-08: 5 | 5
Further studied about the D3 and pie chart |  | 2020-04-09: 5 | 5
Fixed bug on git |  | 2020-04-10: 3 | 3
Fixed D3.js bug |  | 2020-04-10: 4 | 4
Fixed design on the initial design | [31 empty] | 1 | bar: 2020-04-10
Integrated the JSON data from javaspring code to JS and to HTML |  | 2020-04-10: 4 | 4
Improve the initial design to display more data |  | 2020-04-13: 4 | 4
Researched other admin dashboard to gain idea on design |  | 2020-04-13: 4 | 4
Fixed git problem | [31 empty] | 1 | bar: 2020-04-13
Input a specific data on the database to study more on the calculation of time |  | 2020-04-14: 3 | 3
Further studied randomizer for SQL to use on query to populate data |  | 2020-04-14: 2 | 2
Fixed database problem |  | 2020-04-14: 4 | 4
Continuation of fixing database problem |  | 2020-04-15: 3 | 3
Recreated the database and tables |  | 2020-04-15: 2 | 2
Repopulated the tables(inventory table, event table(except the date and time) |  | 2020-04-15: 5 | 5
Researched more about the queries that can be used to populate the data on tables |  | 2020-04-16: 6 | 6
coded query and troubleshoot laptop |  | 2020-04-16: 5 | 5
researched about what API to use for the daterange picker and coded |  | 2020-04-16: 2 | 2
Populated availability table |  | 2020-04-17: 10 | 10
Coded the query to be use for the default website |  | 2020-04-20: 8 | 8
Fixed the buged in availability table and double check each terminal |  | 2020-04-20: 4 | 4
Recalculated the duration_sec column and availability_percentage |  | 2020-04-21: 4 | 4
Inserted and updated the availability table | [31 empty] | 1 | bar: 2020-04-21
Coded the updated query to be use for the default webpage and dateranged webpage |  | 2020-04-21: 5 | 5
Coded the default and date range webpage with the use of the updated query |  | 2020-04-21: 8 | 8
Fixed bugs found on the sonar scan |  | 2020-04-22: 2 | 2
Rewritten the query to be use for the default webpage and dateranged webpaged |  | 2020-04-22: 7 | 7
Kept coding to query to be use while thinking of chart to use for the system |  | 2020-04-23: 5 | 5
Coded the line chart in the dummy webpage for testing and experimenting |  | 2020-04-23: 4 | 4
Implemented line chart in the system but won't show |  | 2020-04-23: 4 | 4
Updated the inventory table in the database to put ISO code. (randomly) Not all ISO code was inputted |  | 2020-04-23: 3 | 3
Updated the query to show only the region code with the highest availability |  | 2020-04-24: 3 | 3
Coded the default and date range webpage with the updated query |  | 2020-04-24: 2 | 2
Coded the bug in line chart and continue analyzing for the solution found on the error |  | 2020-04-27: 8 | 8
Researched about the line chart and ways of coding it and coded on the dummy website |  | 2020-04-27: 4 | 4
Looked for alternative ways of fixing the error on line chart while coding and experimenting the solutions found |  | 2020-04-28: 8 | 8
coded the query for comparing of whole month |  | 2020-04-29: 3 | 3
0
0
Continuation of trying to fix the line chart |  | 2020-04-29: 5 | 5
0
0
0
Reassess the code for line chart |  | 2020-04-30: 4 | 4
0
0
0
Re-coded the line chart and fixed it |  | 2020-04-30: 5 | 5
0
0
0
0
0
0
Meetings |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 1 | 0 | 0 | 1 | 0 | 2.5 | 0 | 2 | 0 | 0 | 1.5 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 12.5
|  | 2020-04-08: 3; 2020-04-10: 1; 2020-04-13: 1; 2020-04-15: 2.5; 2020-04-17: 2; 2020-04-20: 1.5; 2020-04-22: 1; 2020-04-29: 0.5 | 12.5
0
Admin Task |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0
0
Trainings |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0
0
0
Leaves |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Sick Leave | [31 empty] | 0
Vacation Leave | [31 empty] | 0
Mandatory Leave | [31 empty] | 0
Holidays |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0
0
0
0
|  | 8 | 10 | 20 | 4 | 4 | 8 | 19 | 13 | 5 | 13 | 0 | 0 | 10 | 9 | 12.5 | 13 | 12 | 0 | 0 | 13.5 | 18 | 10 | 16 | 5 | 0 | 0 | 8 | 0 | 0.5 | 0 | 231.5